## ROWA_EV
ROWA_EV project planning
Sr No | ECU / Function | SPOC form COC | COC Lead | SPOC Contact number
1 | BCM | RAJASEKHARA REDDY | Himanshu Saxena | 8431433713
2 | PEPS | Rahul Wagh | Himanshu Saxena | 9604068909
3 | TCM | Anit Acharya | Anubhavkumar Singh | 9418719000
4 | IPC | Rajesh Patil | Sanjay Jaisingh | 8600275369
5 | FATC | HANMANT PATIL | Sanjay Jaisingh | 9049318241
6 | HU | Rahul More
7 | AB12 | MOHD SAQIB | Sanjeev Maralihalli | 8669679263
8 | PDC | Sandip Kale |  | 7020820167
9 | SVS | Sanjay Patel |  | 8380052001
10 | EPAS | Rajath Agumbe |  | 9527474900
11 | WPC | Chetan Hinganikar | Himanshu Saxena | 8600942247
12 | EMS - Petrol | Yeshwant Jadhav |  | 8805471300
13 | EMS - Diesel | Yogesh Jadhav |  | 7276079846
14 | ESP | Saurav Patil

## Input Documents tracker
ROWA_EV Project input Documents
Sr No | Document name | COC | SPOC | SPOC Contact number | Data loaction | Document Version | Status | Remark
1 | Feature list | EE Integration |  | 8208105748 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/8. Feature List/1. Feature list
2 | PMXU | EE Integration |  | 8208105748 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/13. PMXU
3 | EEBOM | Arch COC |  | 8888284233 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/1. BOM/1. Labcar BOM/ROWA_LABCAR_EEBOM_v2.xlsx
4 | Non EEBOM | EE Integration |  | 8208105748
5 | Wiring Harness Matrix | EE Integration / WH |  | 7796623958/
6 | Circuit Schematic | EE Integration / WH |  | 7796623958/ | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/5. Circuit Diagram/1. Circuit diagram
7 | Wiring harness drawings | EE Integration / WH |  | 7796623958/ | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/7. Wiring Harness
8 | FIP | Arch COC | Tushar Sayyar | 8888284233
9 | Logical Schematic | Arch COC | Tushar Sayyar | 8888284233 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/23. Q5 FP24/2. Requirement/5. Circuit Diagram/2. Logical Schematic
10 | Vehicle CAN DBC | IVN COC | Vijay Soren | 7873672829 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/3. IVN database/1. CAN
11 | Dynamic HIL requirement | Labcar & HIL | Omkar Kambli | 7358556730
12 | Beta Vehicle build plan | EE Integration | Jayesh Kini | 8788518773
13 | Software Maturation Timeplan | EE Integration | Noopur Sharma | 9999134473
14 | Q Current Document | Arch COC | Tushar Sayyar | 8888284233

## Project tracker
ROWA_EV project planning
Sr No | ECU / Function | SPOC form COC | SPOC Contact number | File / Data loaction | Validation scope confirmation from COC status | DVP SVN Path | Information updation in Validation Scope Document | Remark
1 | BCM |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/1. BCM
2 | PEPS | Rahul Wagh | 9604068909 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/2. PEPS
3 | TCM | YOGENDRA GOYAL | 7276092719 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/14. TELEMATICS
4 | IPC | Rajesh Patil | 8600275369 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/5. IPC
5 | FATC | HANMANT PATIL | 9049318241 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/9. FATC
6 | HU | Abhijit Salunkhe | 9604303146 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
7 | AB12 | MOHD SAQIB | 8669679263 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/6. Airbag
8 | PDC | Sandip Kale | 7020820167 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/17. PDC
9 | SVS | Sanjay Patel | 8380052001 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
10 | EPAS | Rajath Agumbe | 9527474900 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/8. EPAS
11 | WPC | Chetan Hinganikar | 8600942247 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
12 | VCU |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/3. VCU
13 | SASS |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/15. SASS
14 | APA |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/16. APA
15 | ESP | TBC |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/7. ABS_ESP

## FEATURE
Row Labels | Sum of No. of Test cases
BrakeLamps & CHMSL | 65
Grand Total | 65
Add PASS,FAIL,NA,NO
Add ECU
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## CONTROLLER ECU
Row Labels | Sum of No. of Test cases
CCM | 1646
User Input Control | 1283
Partner ECU | 319
FATC Functions | 0
FATC Acceptance Testing | 44
Grand Total | 1646
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Pass (hidden)
Row Labels | Sum of No. of Test cases
Airbag | 1744
(blank) | 1744
(blank) | 1744
(blank) | 1744
(blank) | 1744
Grand Total | 1744
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## PASSFAIL
Row Labels
BCM
Count of PASS | 33
Count of FAIL | 50
Count of NOT TESTED | 1
Count of NA | 2
Total Count of PASS | 33
Total Count of FAIL | 50
Total Count of NOT TESTED | 1
Total Count of NA | 2
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## ROWA_EV_Validation_Plan
P/A/U | Sl. No | Controller ECU | Partner ECU | Features | DVP Name | No. of Test cases | PASS | FAIL | NOT TESTED | NA | No of Days Required | Start Date | End Date | Status | Remarks
P | 1 | NA | NA | Labcar Build | Not Applicable | NA |  |  |  |  | NA | 2024-12-23 | 2024-12-31
A | [11 empty] | 2024-12-23 | 2024-12-31 | 100%
P | 2 | NA | NA | Wiring Harness Updation | Not Applicable | NA |  |  |  |  | NA | 2024-12-31
A | [13 empty] | 90%
P | 3 | NA | NA | Labcar Build Check list | ROWA_Labcar build Checkilst | NA |  |  |  |  | NA | 2025-01-08 | 2025-01-09
A | [13 empty] | 100%
P | 4 | NA | NA | ECU software flashing and parameterisation | Not Applicable | NA |  |  |  |  | NA | 2025-01-06 | 2025-01-14
A | [13 empty] | 100%
P | 5 | NA | NA | Electrical check list | ROWA_Electrical Check list | NA |  |  |  |  | NA | 2025-01-20 | 2025-01-20
A | [13 empty] | 100%
P | 6 | NA | NA | Issue debugging and rectification | Not Applicable | NA |  |  |  |  | NA | 2025-01-31 | 2025-03-13
A | [13 empty] | 100%
P | 7 | NA | NA | Q current measurement ( Labcar & Individual ECU wise) | Not Applicable | NA |  |  |  |  | NA | NA | NA
A | [13 empty] | 100%
P | 8 | IVN | NA | IVN Acceptance Testing | Not Available | NA |  |  |  |  | NA | NA | NA
A | [13 empty] | 100%
P | 9 | BCM | CDC | Position Lights_Reg platelamp_s | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 18 |  |  |  |  | 0.25714 | 2025-02-03 | 2025-02-03 06:14
A
P | 10 | BCM | CDC | Lane Changer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 18 | 15 |  |  |  | 0.25714 | 2025-02-04 06:14 | 2025-02-04 12:29
A
P | 11 | BCM | CDC | Turn Indicator | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 17 | 8 |  |  |  | 0.24286 | 2025-02-05 12:29 | 2025-02-05 18:14
A
P | 12 | BCM | CDC | Hazard | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 17 | 20 |  |  |  | 0.24286 | 2025-02-06 18:14 | 2025-02-07
A
P | 13 | BCM | CDC | DRL | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls |  | 20 |  |  |  |  | 2025-02-08
A
P | 14 | BCM |  | Welcome Goodbye | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls |  | 0
A | [13 empty] | 100%
P | 15 | BCM | CDC | Low_Beam | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls |  | 16
A
P | 16 | BCM | CDC | High_Beam | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls |  | 22
A
P | 17 | BCM | CDC | Flash_To_Pass | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429
A
P | 18 | BCM | CDC | Head_Lamp_leveling | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 32 | 32 |  |  |  | 0.45714
A
P | 19 | BCM |  | Auto_Head Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429
A
P | 20 | BCM |  | Roof_Boot_KRI_Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 26 | 26 |  |  |  | 0.37143
A | [13 empty] | 100%
P | 21 | BCM |  | Glove Box Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 16 | 16 |  |  |  | 0.22857
A | [13 empty] | 5%
P | 22 | BCM |  | Window_Winding | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 36 | 36 |  |  |  | 0.51429
A | [13 empty] | 100%
P | 23 | BCM |  | Approach Light | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 26 | 26 |  |  |  | 0.37143
A
P | 24 | BCM |  | Vehicle Seek | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 | 6 |  |  |  | 0.085714
A
P | 25 | BCM |  | Fr Fog Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 40 | 40 |  |  |  | 0.57143
A
P | 26 | BCM |  | RR Fog Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 | 4 |  |  |  | 0.057143
A
P | 27 | BCM |  | Cornering Function | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 | 4 |  |  |  | 0.057143
A
P | 28 | BCM |  | Stop Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 39 | 39 |  |  |  | 0.55714
A
P | 29 | BCM |  | Horn | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 18 | 18 |  |  |  | 0.25714
A
P | 30 | BCM | CDC | Perimetric | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 28 | 28 |  |  |  | 0.4
A
P | 31 | BCM | CDC | Force Panic | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 | 4 |  |  |  | 0.057143
A
P | 32 | BCM |  | Vehicle Mislock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 12 | 12 |  |  |  | 0.17143
A
P | 33 | BCM |  | Puddle | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429
A | [13 empty] | 100%
P | 34 | BCM |  | Sunvisor Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429
A
P | 35 | BCM |  | Hardware Wakeup | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 7 | 7 |  |  |  | 0.1
A
P | 36 | BCM |  | BCM UCS | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 10 | 10 |  |  |  | 0.14286
A
P | 37 | BCM |  | WiperLow Speed | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  | 8 |  |  | 0.11429
A | [13 empty] | 100%
P | 38 | BCM |  | Wiper High Speed | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  | 8 |  |  | 0.11429
A | [13 empty] | 100%
P | 39 | BCM |  | Wiper flick | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 12 |  | 12 |  |  | 0.17143
A | [13 empty] | 100%
P | 40 | BCM |  | Front Washer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 |  | 6 |  |  | 0.085714
A | [13 empty] | 100%
P | 41 | BCM |  | Rear Washer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 |  | 6 |  |  | 0.085714
A | [13 empty] | 100%
P | 42 | BCM |  | Lock Unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 36 |  | 36 |  |  | 0.51429
A
P | 43 | BCM |  | Tail gate unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 24 |  | 24 |  |  | 0.34286
A
P | 44 | BCM | CCM | Express Cooling | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 24 |  | 24 |  |  | 0.34286
A
P | 45 | BCM | AB12, CDC | Crash Unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 |  | 4 |  |  | 0.057143
A
P | 46 | BCM |  | Batt Saver | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 20 |  | 20 |  |  | 0.28571
A | [13 empty] | 100%
P | 47 | CCM |  | FATC Acceptance Testing | Not Available | 44 |  | 44 |  |  | 0.62857
A | [13 empty] | 100%
P | 48 | CDC |  | CDC Acceptance Testing | Not Available
A | [13 empty] | 100%
P | 49 | BCM |  | ORVM Feature settiong on HU | ORVM_Auto_Unfold_Feature_settings on HU_DVP_V0.4.xlsx | 29 |  | 29 |  |  | 0.41429 |  | 2025-02-03 06:14
A
P | 50 | BCM |  | ORVM Fold_Unfold | 15-TML_X451_Q5_Labcar_ORVM_DVP_V1.7.xlsx | 92 |  | 92 |  |  | 1.3143 | 2025-02-04 06:14 | 2025-02-05 13:41
A
P | 51 | BCM |  | FWLH | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 16 |  | 16 |  |  | 0.22857 | 2025-02-06 13:41 | 2025-02-06 19:12
A | [13 empty] | 100%
P | 52 | BCM |  | FWAD | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 9 |  | 9 |  |  | 0.12857 | 2025-02-07 19:12 | 2025-02-07 22:19
A | [13 empty] | 100%
P | 53 | BCM |  | RWC | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 6 |  | 6 |  |  | 0.085714 | 2025-02-08 22:19 | 2025-02-09 00:29
A | [13 empty] | 100%
P | 54 | BCM |  | RWSC | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 6 |  | 6 |  |  | 0.085714 | 2025-02-10 00:29 | 2025-02-10 02:38
A
P | 55 | BCM |  | Roof Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 43 |  | 43 |  |  | 0.61429 | 2025-02-11 02:38 | 2025-02-11 17:17
A | [13 empty] | 100%
P | 56 | BCM |  | Glove Box Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 36 |  | 36 |  |  | 0.51429 | 2025-02-12 17:17 | 2025-02-13 05:31
A | [13 empty] | 100%
P | 57 | BCM |  | Puddle Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 36 |  | 36 |  |  | 0.51429 | 2025-02-14 05:31 | 2025-02-14 17:46
A | [13 empty] | 100%
P | 58 | BCM |  | Boot Lamp 1 | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 41 |  | 41 |  |  | 0.58571 | 2025-02-15 17:46 | 2025-02-16 07:55
A | [13 empty] | 100%
P | 59 | BCM |  | Ambient Lighting | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 73 |  | 73 |  |  | 1.0429 | 2025-02-17 07:55 | 2025-02-18 08:53
A
P | 60 | BCM |  | Turn indicators & Hazards | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 161 |  | 161 |  |  | 2.3 | 2025-02-19 08:53 | 2025-02-21 16:05
A
P | 61 | BCM |  | Position Lamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 64 |  | 64 |  |  | 0.91429 | 2025-02-22 16:05 | 2025-02-23 13:55
A
P | 62 | BCM |  | LaneChanger | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 44 |  | 44 |  |  | 0.62857 | 2025-02-24 13:55 | 2025-02-25 05:02
A
P | 63 | BCM |  | Headlamp LowBeam | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 42 |  | 42 |  |  | 0.6 | 2025-02-26 05:02 | 2025-02-26 19:26
A
P | 64 | BCM |  | Headlamp HighBeam | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 54 |  | 54 |  |  | 0.77143 | 2025-02-27 19:26 | 2025-02-28 13:55
A
P | 65 | BCM |  | BrakeLamps & CHMSL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 65 |  | 65 |  |  | 0.92857 | 2025-03-01 13:55 | 2025-03-02 12:14
A
P | 66 | BCM |  | FrontFogLamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 62 |  | 62 |  |  | 0.88571 | 2025-03-03 12:14 | 2025-03-04 09:36
A
P | 67 | BCM |  | RearFogLamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 56 |  | 56 |  |  | 0.8 | 2025-03-05 09:36 | 2025-03-06 04:48
A
P | 68 | BCM |  | ApproachLights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 39 |  | 39 |  |  | 0.55714 | 2025-03-07 04:48 | 2025-03-07 18:14
A
P | 69 | BCM |  | Daytime Running Lights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 113 |  | 113 |  |  | 1.6143 | 2025-03-08 18:14 | 2025-03-10 08:53
A
P | 70 | BCM |  | CorneringLamp | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 210 |  | 210 |  |  | 3 | 2025-03-11 08:53 | 2025-03-14 08:53
A
P | 71 | BCM |  | Reverse Lights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 76 |  | 76 |  |  | 1.0857 | 2025-03-15 08:53 | 2025-03-16 11:02
A
P | 72 | BCM |  | AHL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 10 |  | 10 |  |  | 0.14286 | 2025-03-17 11:02 | 2025-03-17 14:24
A
P | 73 | BCM |  | SBL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 11 |  | 11 |  |  | 0.15714 | 2025-03-18 14:24 | 2025-03-18 18:14
A
P | 74 | BCM |  | FRONT ADAS | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 19 |  | 19 |  |  | 0.27143 | 2025-03-19 18:14 | 2025-03-20 00:43
A
P | 75 | BCM |  | REAR ADAS | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 30 |  | 30 |  |  | 0.42857 | 2025-03-21 00:43 | 2025-03-21 11:02
A
P | 76 | BCM |  | CPL_SOC | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 84 |  | 84 |  |  | 1.2 | 2025-03-22 11:02 | 2025-03-23 15:50
A
P | 77 | BCM |  | Auto Wipe | TML_X451_Q5_X451_BCM_Labcar_Auto_Wipe_DVP_0.4.xlsx | 92 |  | 92 |  |  | 1.3143 | 2025-03-24 15:50 | 2025-03-25 23:17
A | [13 empty] | 100%
P | 78 | BCM | CDC | Press Brake Message | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 33 |  | 33 |  |  | 0.47143 | 2025-03-26 23:17 | 2025-03-27 10:34
A
P | 79 | BCM | CDC | ACC ON Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 42 |  | 42 |  |  | 0.6 | 2025-03-28 10:34 | 2025-03-29 00:58
A
P | 80 | BCM | CDC | IGN ON Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 42 |  | 42 |  |  | 0.6 | 2025-03-30 00:58 | 2025-03-30 15:22
A
P | 81 | BCM | CDC | WelCome Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 22 |  | 22 |  |  | 0.31429 | 2025-03-31 15:22 | 2025-03-31 22:48
A
P | 82 | BCM | CDC | Audio Warning | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 44 |  | 44 |  |  | 0.62857 | 2025-04-01 22:48 | 2025-04-02 13:55
A
P | 83 | BCM |  | DriverWindow_Integration_In_BCM | TML_X451_Q5_Labcar_DriverWindow_Integration_In_BCM_DVP_V1.2_21-06-24.xls | 92 |  | 92 |  |  | 1.3143 | 2025-04-03 13:55 | 2025-04-04 21:22
A | [13 empty] | 100%
P | 84 | BCM |  | AutoPinchGeneral | TE_TML_X451_BCM_Labcar_AntiPinch_DVP_V1.3_9Feb'24.xls | 69 |  | 69 |  |  | 0.98571 | 2025-04-05 21:22 | 2025-04-06 21:07
A
P | 85 | BCM | CDC | Clamp Control for EV | TML_Labcar_Clamp_Control_DVP_V3.9_21-06-24.xlsx | 186 |  | 186 |  |  | 2.6571 | 2025-04-07 21:07 | 2025-04-10 12:58
A
P | 86 | BCM | CDC | Passive_EntryExit | TML_Labcar_PassiveEntryExit_DVP_V3.6.xlsx | 581 | 76 | 581 |  |  | 8.3 | 2025-04-11 12:58 | 2025-04-19 20:10
A
P | 87 | BCM | CDC | Passive_Tailgate_Control | TML_Labcar_PassiveTailgateControl_DVP_V3.3.xlsx | 57 | 35 | 57 |  |  | 0.81429 | 2025-04-20 20:10 | 2025-04-21 15:36
A
P | 88 | BCM |  | Passive_Start_EV | TML_Labcar_PassiveStart_DVP_V3.9.xlsx | 174 | 98 | 174 |  |  | 2.4857 | 2025-04-22 15:36 | 2025-04-25 03:22
A
P | 89 | SASS | BCM | BCM Functional Zones | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 23 |  |  | 23 |  | 0.32857 | 2025-04-26 03:22 | 2025-04-26 11:17 |  | SASS TC partially testable on LABCAR
A
P | 90 | SASS | BCM | BCM General Req | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 178 |  |  | 178 |  | 2.5429 | 2025-04-27 11:17 | 2025-04-30 00:14 |  | SASS TC partially testable on LABCAR
A
P | 91 | SASS | BCM | BCM Driver Passenger Unlock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 175 |  |  | 175 |  | 2.5 | 2025-05-01 00:14 | 2025-05-03 12:14 |  | SASS TC partially testable on LABCAR
A
P | 92 | SASS | BCM | BCM Driver Passenger Lock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 629 |  |  | 629 |  | 8.9857 | 2025-05-04 12:14 | 2025-05-13 12:00 |  | SASS TC partially testable on LABCAR
A
P | 93 | SASS | BCM | BCM Tailgate Unlock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 176 |  |  | 176 |  | 2.5143 | 2025-05-14 12:00 | 2025-05-17 00:14 |  | SASS TC partially testable on LABCAR
A
P | 94 | SASS | BCM | BCM Auto Learning | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 4 |  |  | 4 |  | 0.057143 | 2025-05-18 00:14 | 2025-05-18 01:41 |  | SASS TC partially testable on LABCAR
A
P | 95 | SASS | BCM | BCM Vehicle Start Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 75 |  |  | 75 |  | 1.0714 | 2025-05-19 01:41 | 2025-05-20 03:22 |  | SASS TC partially testable on LABCAR
A
P | 96 | SASS | BCM | BCM RKE Function | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 285 |  |  | 285 |  | 4.0714 | 2025-05-21 03:22 | 2025-05-25 05:02 |  | SASS TC partially testable on LABCAR
A
P | 97 | SASS | BCM | BCM WelcomeLight Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 17 |  |  | 17 |  | 0.24286 | 2025-05-26 05:02 | 2025-05-26 10:48 |  | SASS TC partially testable on LABCAR
A
P | 98 | SASS | BCM | BCM FollowMeHome Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 17 |  |  | 17 |  | 0.24286 | 2025-05-27 10:48 | 2025-05-27 16:34 |  | SASS TC partially testable on LABCAR
A
P | 99 | SASS | BCM | BCM Personalization Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 91 |  |  | 91 |  | 1.3 | 2025-05-28 16:34 | 2025-05-29 23:46 |  | SASS TC partially testable on LABCAR
A
P | 100 | SASS | BCM | BCM POT Opening | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 63 |  |  | 63 |  | 0.9 | 2025-05-30 23:46 | 2025-05-31 21:22 |  | SASS TC partially testable on LABCAR
A
P | 101 | SASS | BCM | BCM POT Closing | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 63 |  |  | 63 |  | 0.9 | 2025-06-01 21:22 | 2025-06-02 18:58 |  | SASS TC partially testable on LABCAR
A
P | 102 | SASS | BCM | BCM POT UID Fun Disabled | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 4 |  |  | 4 |  | 0.057143 | 2025-06-03 18:58 | 2025-06-03 20:24 |  | SASS TC partially testable on LABCAR
A
P | 103 | SASS | BCM | BCM POT openingPEPSTailgateSwtc | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 33 |  |  | 33 |  | 0.47143 | 2025-06-04 20:24 | 2025-06-05 07:41 |  | SASS TC partially testable on LABCAR
A
P | 104 | SASS | BCM | BCM POT closingPEPSTailgateSwtc | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 33 |  |  | 33 |  | 0.47143 | 2025-06-06 07:41 | 2025-06-06 18:58 |  | SASS TC partially testable on LABCAR
A
P | 105 | SASS | BCM | PEPS Tailgate Trigger SASS-BCM | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 57 |  |  | 57 |  | 0.81429 | 2025-06-07 18:58 | 2025-06-08 14:24 |  | SASS TC partially testable on LABCAR
A
P | 106 | SASS | BCM | POT OpeningThroughFasciaSwitch | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 35 |  |  | 35 |  | 0.5 | 2025-06-09 14:24 | 2025-06-10 02:24 |  | SASS TC partially testable on LABCAR
A
P | 107 | SASS | BCM | POT ClosingThroughFasciaSwitch | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 30 |  |  | 30 |  | 0.42857 | 2025-06-11 02:24 | 2025-06-11 12:43 |  | SASS TC partially testable on LABCAR
A
P | 108 | SASS | BCM | Operating Voltage Range | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 6 |  |  | 6 |  | 0.085714 | 2025-06-12 12:43 | 2025-06-12 14:53 |  | SASS TC partially testable on LABCAR
A
P | 109 | SASS | BCM | Power_Consumption | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 9 |  |  | 9 |  | 0.12857 | 2025-06-13 14:53 | 2025-06-13 18:00 |  | SASS TC partially testable on LABCAR
A
P | 110 | SASS | BCM | General_Requirements | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 13 |  |  | 13 |  | 0.18571 | 2025-06-14 18:00 | 2025-06-14 22:34 |  | SASS TC partially testable on LABCAR
A
P | 111 | SASS | BCM | _Normal_Mode | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 7 |  |  | 7 |  | 0.1 | 2025-06-15 22:34 | 2025-06-16 00:58 |  | SASS TC partially testable on LABCAR
A
P | 112 | SASS | BCM | Lock_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 |  |  | 24 |  | 0.34286 | 2025-06-17 00:58 | 2025-06-17 09:07 |  | SASS TC partially testable on LABCAR
A
P | 113 | SASS | BCM | Unlock_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 |  |  | 24 |  | 0.34286 | 2025-06-18 09:07 | 2025-06-18 17:17 |  | SASS TC partially testable on LABCAR
A
P | 114 | SASS | BCM | Approach_Light_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 23 |  |  | 23 |  | 0.32857 | 2025-06-19 17:17 | 2025-06-20 01:12 |  | SASS TC partially testable on LABCAR
A
P | 115 | SASS | BCM | Tailgate_Unlock_Function_ | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 |  |  | 24 |  | 0.34286 | 2025-06-21 01:12 | 2025-06-21 09:22 |  | SASS TC partially testable on LABCAR
A
P | 116 | SASS | BCM | Tailgate_Open_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 |  |  | 24 |  | 0.34286 | 2025-06-22 09:22 | 2025-06-22 17:31 |  | SASS TC partially testable on LABCAR
A
P | 117 | SASS | BCM | Force_Panic_Scenarios_ | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 25 |  |  | 25 |  | 0.35714 | 2025-06-23 17:31 | 2025-06-24 02:10 |  | SASS TC partially testable on LABCAR
A
P | 118 | SASS | BCM | Operating_Modes | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 6 |  |  | 6 |  | 0.085714 | 2025-06-25 02:10 | 2025-06-25 04:19 |  | SASS TC partially testable on LABCAR
A
P | 119 | SASS | BCM | Vehicle Start Stop Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 172 |  |  | 172 |  | 2.4571 | 2025-06-26 04:19 | 2025-06-28 15:22 |  | SASS TC partially testable on LABCAR
A
P | 120 | SASS | BCM | Welcome Lighting Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 91 |  |  | 91 |  | 1.3 | 2025-06-29 15:22 | 2025-06-30 22:34 |  | SASS TC partially testable on LABCAR
A
P | 121 | SASS | BCM | Follow-Me Home Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 70 |  |  | 70 |  | 1 | 2025-07-01 22:34 | 2025-07-02 22:34 |  | SASS TC partially testable on LABCAR
A
P | 122 | SASS | BCM | SASS BCM Autolearning | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 9 |  |  | 9 |  | 0.12857 | 2025-07-03 22:34 | 2025-07-04 01:41 |  | SASS TC partially testable on LABCAR
A
P | 123 | SASS | BCM | KeyFob Vehicle Lock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 116 |  |  | 116 |  | 1.6571 | 2025-07-05 01:41 | 2025-07-06 17:31 |  | SASS TC partially testable on LABCAR
A
P | 124 | SASS | BCM | KeyFob Vehicle Unlock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 68 |  |  | 68 |  | 0.97143 | 2025-07-07 17:31 | 2025-07-08 16:48 |  | SASS TC partially testable on LABCAR
A
P | 125 | SASS | BCM | KeyFob Approch Light | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 18 |  |  | 18 |  | 0.25714 | 2025-07-09 16:48 | 2025-07-09 23:02 |  | SASS TC partially testable on LABCAR
A
P | 126 | SASS | BCM | KeyFob Tailgate Unlock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 86 |  |  | 86 |  | 1.2286 | 2025-07-10 23:02 | 2025-07-12 04:34 |  | SASS TC partially testable on LABCAR
A
P | 127 | SASS | BCM | Keyfob Force Panic | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 9 |  |  | 9 |  | 0.12857 | 2025-07-13 04:34 | 2025-07-13 07:41 |  | SASS TC partially testable on LABCAR
A
P | 128 | BCM | ESCL | ESCL | TML_Labcar_ESCL_DVP_V4.0_20May24.xls | 186 | 87 |  | 186 |  | 2.6571 | 2025-07-14 07:41 | 2025-07-16 23:31
A
P | 129 | CCM | CDC | User Input Control | TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx | 1283 |  |  | 1283 |  | 18.3286 | 2025-07-17 23:31 | 2025-08-05 07:26
A | [13 empty] | 100%
P | 130 | CCM | CDC | FATC Functions | TML_Gen3_CCM_DVP_V1.0.xlsx | 0 |  |  | 0 |  | 0 | 2025-08-06 07:26 | 2025-08-06 07:26
A
P | 131 | CCM | CDC | Partner ECU | TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx | 319 |  |  | 319 |  | 4.5571 | 2025-08-07 07:26 | 2025-08-11 20:53
A | [13 empty] | 100%
P | 132 | CDC |  | Door_Ajar_Mid_Variant | TML_IPC_Door_Ajar_with_Bonnet_TC_v2.0.xlsx | 263 |  |  | 263 |  | 3.7571 | 2025-08-12 20:53 | 2025-08-16 15:07
A | [13 empty] | 20%
P | 133 | CDC | BCM | High Beam-CAN | TML_IPC_HighBeam_TC_v2.0.xlsx | 31 |  |  |  | 31 | 0.44286 | 2025-08-17 15:07 | 2025-08-18 01:41
A
P | 134 | CDC | BCM | High Beam-Hardware | TML_IPC_HighBeam_TC_v2.0.xlsx | 0 |  |  |  | 0 | 0 | 2025-08-19 01:41 | 2025-08-19 01:41 |  | NA
A
P | 135 | CDC | BCM | Text Alert High Beam-CAN | TML_IPC_HighBeam_TC_v2.0.xlsx | 7 |  |  |  | 7 | 0.1 | 2025-08-20 01:41 | 2025-08-20 04:05
A
P | 136 | CDC | BCM | Text Alert High Beam- Hardware | TML_IPC_HighBeam_TC_v2.0.xlsx | 0 |  |  |  | 0 | 0 | 2025-08-21 04:05 | 2025-08-21 04:05 |  | NA
A
P | 137 | CDC | BCM | Position_Lamp | TML_IPC_PositionLamp_DVP_v2.0 .xlsx | 39 |  |  |  | 39 | 0.55714 | 2025-08-22 04:05 | 2025-08-22 17:31
100%
P | 138 | CDC | BCM | Text Alert | TML_IPC_PositionLamp_DVP_v2.0 .xlsx | 40 |  |  |  | 40 | 0.57143 | 2025-08-23 17:31 | 2025-08-24 07:12
100%
P | 139 | CDC |  | PowerModes | TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx | 0 |  |  |  | 0 | 0 | 2025-08-25 07:12 | 2025-08-25 07:12 |  | NA
P | 140 | CDC |  | WakeUP | TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx | 0 |  |  |  | 0 | 0 | 2025-08-26 07:12 | 2025-08-26 07:12 |  | NA
P | 141 | CDC | BCM | Turn_Left_Indicator | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 26 |  |  |  | 26 | 0.37143 | 2025-08-27 07:12 | 2025-08-27 16:05
P | 142 | CDC | BCM | Turn_Right_Indicator | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 26 |  |  |  | 26 | 0.37143 | 2025-08-28 16:05 | 2025-08-29 00:58
P | 143 | CDC | BCM | Hazard | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 25 |  |  |  | 25 | 0.35714 | 2025-08-30 00:58 | 2025-08-30 09:36
P | 144 | CDC |  | Wireless Power Charger(10.25") | TML_IPC_Wireless_Power_Charger_TC_v1.0.xlsx | 52 |  |  |  | 52 | 0.74286 | 2025-08-31 09:36 | 2025-09-01 03:22
[14 empty] | 100% | Completed in Sierra
P | 145 | Airbag |  | DID401A-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 60 |  |  |  | 75 | 0.85714 | 2025-09-02 03:22 | 2025-09-03
100%
P | 147 | Airbag |  | DID401A-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 60 |  |  |  | 60 | 0.85714 | 2025-09-04 | 2025-09-04 20:38
100%
P | 148 | Airbag |  | DID401A-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 77 |  |  |  | 77 | 1.1 | 2025-09-05 20:38 | 2025-09-06 23:02
100%
P | 149 | Airbag |  | DID401A-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 33 |  |  |  | 33 | 0.47143 | 2025-09-07 23:02 | 2025-09-08 10:19
100%
P | 150 | Airbag |  | DID401B-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 |  |  |  | 171 | 2.4429 | 2025-09-09 10:19 | 2025-09-11 20:53
100%
P | 151 | Airbag |  | DID401B-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 |  |  |  | 171 | 2.4429 | 2025-09-12 20:53 | 2025-09-15 07:26
100%
P | 152 | Airbag |  | DID401B-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 126 |  |  |  | 126 | 1.8 | 2025-09-16 07:26 | 2025-09-18 02:38
100%
P | 153 | Airbag |  | DID401B-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 279 |  |  |  | 279 | 3.9857 | 2025-09-19 02:38 | 2025-09-23 02:24
100%
P | 154 | Airbag |  | DID401B-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-09-24 02:24 | 2025-09-24 02:24 |  | NA
P | 155 | Airbag |  | DID401B-06 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-09-25 02:24 | 2025-09-25 02:24 |  | NA
P | 156 | Airbag |  | DID401B-07 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-09-26 02:24 | 2025-09-26 02:24 |  | NA
P | 157 | Airbag |  | DID401B-08 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-09-27 02:24 | 2025-09-27 02:24 |  | NA
P | 158 | Airbag |  | DID401B-09 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-09-28 02:24 | 2025-09-28 02:24 |  | NA
P | 159 | Airbag |  | DID401B-0A | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 81 |  |  |  | 81 | 1.1571 | 2025-09-29 02:24 | 2025-09-30 06:14
100%
P | 160 | Airbag |  | DID401B-0B | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 156 |  |  |  | 156 | 2.2286 | 2025-10-01 06:14 | 2025-10-03 11:46
100%
P | 161 | Airbag |  | DID401B-0C | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 |  |  |  | 129 | 1.8429 | 2025-10-04 11:46 | 2025-10-06 07:55 |  | NA
100%
P | 162 | Airbag |  | DID401B-0D | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 |  |  |  | 129 | 1.8429 | 2025-10-07 07:55 | 2025-10-09 04:05 |  | NA
100%
P | 163 | Airbag |  | DID401B-0E | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 110 |  |  |  | 108 | 1.5714 | 2025-10-10 04:05 | 2025-10-11 17:46 |  | NA
100%
P | 164 | Airbag |  | DID401B-0F | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  |  | 0 | 0 | 2025-10-12 17:46 | 2025-10-12 17:46 |  | NA
P | 165 | Airbag |  | Func-SysWL | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 6 |  |  |  | 6 | 0.085714 | 2025-10-13 17:46 | 2025-10-13 19:55 |  | NA
P | 166 | Airbag |  | Func-PADS-PADI | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 28 |  |  |  | 28 | 0.4 | 2025-10-14 19:55 | 2025-10-15 05:31
100%
P | 167 | Airbag | BCM | DTC | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 130 |  |  |  | 130 | 1.8571 | 2025-10-16 05:31 | 2025-10-18 02:10
P |  | SZM | BCM | Squab_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  |  | 95 | 1.3571 | 2025-10-19 02:10 | 2025-10-20 10:48
100%
P |  | SZM | BCM | Slide_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  |  | 95 | 1.3571 | 2025-10-21 10:48 | 2025-10-22 19:26
100%
P |  | SZM | BCM | Height_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  |  | 95 | 1.3571 | 2025-10-23 19:26 | 2025-10-25 04:05
100%
P |  | SZM | BCM | MemoryRecallStore | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 91 |  |  |  | 91 | 1.3 | 2025-10-26 04:05 | 2025-10-27 11:17 |  | DVP needs to be updated
P |  | SZM | BCM | DTC | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 43 |  |  |  | 43 | 0.61429 | 2025-10-28 11:17 | 2025-10-29 01:55 |  | DVP needs to be updated
P |  | SZM | BCM | EEE | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 12 |  |  |  | 12 | 0.17143 | 2025-10-30 01:55 | 2025-10-30 06:00 |  | DVP needs to be updated
|  | BCM |  | T_Logo | Switch illumination DVP_T_Logo_BCMC41_4_CW08.xlsx | 88 | 98 |  |  | 88 | 1.2571 | 2025-10-31 06:00 | 2025-11-01 12:14
|  | BCM |  | Perimeter Alarm | TML_X451_Q5_Labcar_Alarm_&_Security_DVP_2.5.xlsx | 87 | 65 |  |  | 87 | 1.2429 | 2025-11-02 12:14 | 2025-11-03 18:00
|  | CDC | BCM | PEPS Indication for IGN | TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx | 23 |  |  |  | 23 | 0.32857 | 2025-11-04 18:00 | 2025-11-05 01:55
|  | CDC | BCM | PEPS Indication for ACC | TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx | 19 |  |  |  | 19 | 0.27143 | 2025-11-06 01:55 | 2025-11-06 08:24
Formulas:
End Date = IF(AND(ISNUMBER([Start Date]), ISNUMBER([No of Days Required])), [Start Date] + ROUND([No of Days Required], 2), "")

## User Notes
| Sr. No. | Notes
| 1 | Do not insert any row or column in the planning sheet.
| 2 | The cells marked with red blocks are to be updated by user.
| 3 | The new tasks are to be added in a sequential manner.
| 4 | For any task there will be two rows : Planned and Actual.
| 5 | The task deferred is to be mentioned in column "Task Deferred"
| 6 | Sundays and Holidays are not considered.
| 7 | There will different worksheets for different vehicle variants.
| 8 | Changes in SW drop will be termed as "Deferred" and new Task will be added with the updated timeline.
| 9 | Unplanned Task will be appended to the list and also have Actual time spent.
147 | DID401A-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 59 | 0.84286 | Airbag
148 | DID401A-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 77 | 1.1 | Airbag | Validation
149 | DID401A-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 33 | 0.47143 | Airbag | Validation
150 | DID401B-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 | 2.4429 | Airbag | Validation
151 | DID401B-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 | 2.4429 | Airbag | Validation
152 | DID401B-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 126 | 1.8 | Airbag | Validation
153 | DID401B-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 279 | 3.9857 | Airbag | Validation
154 | DID401B-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
155 | DID401B-06 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 231 | 3.3 | Airbag | Validation
156 | DID401B-07 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
157 | DID401B-08 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 231 | 3.3 | Airbag | Validation
158 | DID401B-09 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
159 | DID401B-0A | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 81 | 1.1571 | Airbag | Validation
160 | DID401B-0B | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 156 | 2.2286 | Airbag | Validation
161 | DID401B-0C | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
162 | DID401B-0D | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
163 | DID401B-0E | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 108 | 1.5429 | Airbag | Validation
164 | DID401B-0F | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
165 | Func-SysWL | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 6 | 0.085714 | Airbag | Validation
166 | Func-PADS-PADI | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 28 | 0.4 | Airbag | Validation
167 | DTC | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 130 | 1.8571 | Airbag | Validation
Validation
Validation
Validation
Validation
Validation
Validation
Validation
Validation

## DVP_List
Sr. No. | DVP Name and Version | Total No.of test cases | No. of Days require to execute the DVP | Testing Type | Applicable ECU | DVP Prepared By | SVN Link
1