## ROWA_EV
ROWA_EV project planning
Sr No | ECU / Function | SPOC form COC | COC Lead | SPOC Contact number
1 | BCM | RAJASEKHARA REDDY | Himanshu Saxena | 8431433713
2 | PEPS | Rahul Wagh | Himanshu Saxena | 9604068909
3 | TCM | Anit Acharya | Anubhavkumar Singh | 9418719000
4 | IPC | Rajesh Patil | Sanjay Jaisingh | 8600275369
5 | FATC | HANMANT PATIL | Sanjay Jaisingh | 9049318241
6 | HU | Rahul More
7 | AB12 | MOHD SAQIB | Sanjeev Maralihalli | 8669679263
8 | PDC | Sandip Kale |  | 7020820167
9 | SVS | Sanjay Patel |  | 8380052001
10 | EPAS | Rajath Agumbe |  | 9527474900
11 | WPC | Chetan Hinganikar | Himanshu Saxena | 8600942247
12 | EMS - Petrol | Yeshwant Jadhav |  | 8805471300
13 | EMS - Diesel | Yogesh Jadhav |  | 7276079846
14 | ESP | Saurav Patil

## Input Documents tracker
ROWA_EV Project input Documents
Sr No | Document name | COC | SPOC | SPOC Contact number | Data loaction | Document Version | Status | Remark
1 | Feature list | EE Integration |  | 8208105748 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/8. Feature List/1. Feature list
2 | PMXU | EE Integration |  | 8208105748 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/13. PMXU
3 | EEBOM | Arch COC |  | 8888284233 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/1. BOM/1. Labcar BOM/ROWA_LABCAR_EEBOM_v2.xlsx
4 | Non EEBOM | EE Integration |  | 8208105748
5 | Wiring Harness Matrix | EE Integration / WH |  | 7796623958/
6 | Circuit Schematic | EE Integration / WH |  | 7796623958/ | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/5. Circuit Diagram/1. Circuit diagram
7 | Wiring harness drawings | EE Integration / WH |  | 7796623958/ | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/7. Wiring Harness
8 | FIP | Arch COC | Tushar Sayyar | 8888284233
9 | Logical Schematic | Arch COC | Tushar Sayyar | 8888284233 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/23. Q5 FP24/2. Requirement/5. Circuit Diagram/2. Logical Schematic
10 | Vehicle CAN DBC | IVN COC | Vijay Soren | 7873672829 | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/2. Requirement/3. IVN database/1. CAN
11 | Dynamic HIL requirement | Labcar & HIL | Omkar Kambli | 7358556730
12 | Beta Vehicle build plan | EE Integration | Jayesh Kini | 8788518773
13 | Software Maturation Timeplan | EE Integration | Noopur Sharma | 9999134473
14 | Q Current Document | Arch COC | Tushar Sayyar | 8888284233

## Project tracker
ROWA_EV project planning
Sr No | ECU / Function | SPOC form COC | SPOC Contact number | File / Data loaction | Validation scope confirmation from COC status | DVP SVN Path | Information updation in Validation Scope Document | Remark
1 | BCM |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/1. BCM
2 | PEPS | Rahul Wagh | 9604068909 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/2. PEPS
3 | TCM | YOGENDRA GOYAL | 7276092719 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/14. TELEMATICS
4 | IPC | Rajesh Patil | 8600275369 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/5. IPC
5 | FATC | HANMANT PATIL | 9049318241 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/9. FATC
6 | HU | Abhijit Salunkhe | 9604303146 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
7 | AB12 | MOHD SAQIB | 8669679263 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/6. Airbag
8 | PDC | Sandip Kale | 7020820167 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/17. PDC
9 | SVS | Sanjay Patel | 8380052001 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
10 | EPAS | Rajath Agumbe | 9527474900 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/8. EPAS
11 | WPC | Chetan Hinganikar | 8600942247 |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/4. HU
12 | VCU |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/3. VCU
13 | SASS |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/15. SASS
14 | APA |  |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/16. APA
15 | ESP | TBC |  |  |  | https://tmvwsvnsrv.tmindia.tatamotors.com/svn/Labcar-Q5-X4-X1-programs/trunk/19.Rowa/3. Validation/1. DVP/7. ABS_ESP

## Sheet2
Row Labels | Count of Features | Count of No. of Test cases
14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 5 | 5
15-TML_X451_Q5_Labcar_ORVM_DVP_V1.7.xlsx | 1 | 1
Not Applicable | 5 | 5
Not Available | 3 | 2
ORVM_Auto_Unfold_Feature_settings on HU_DVP_V0.4.xlsx | 1 | 1
ROWA_Electrical Check list | 1 | 1
ROWA_Labcar build Checkilst | 1 | 1
Switch illumination DVP_T_Logo_BCMC41_4_CW08.xlsx | 1 | 1
TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 11 | 11
TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx | 2 | 2
TE_TML_X451_BCM_Labcar_AntiPinch_DVP_V1.3_9Feb'24.xls | 1 | 1
TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 4 | 4
TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 5 | 5
TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 19 | 19
TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 38 | 38
TML_Gen3_CCM_DVP_V1.0.xlsx | 1 | 1
TML_IPC_Door_Ajar_with_Bonnet_TC_v2.0.xlsx | 1 | 1
TML_IPC_HighBeam_TC_v2.0.xlsx | 4 | 4
TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx | 2 | 2
TML_IPC_PositionLamp_DVP_v2.0 .xlsx | 2 | 2
TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx | 2 | 2
TML_IPC_TurnIndicator_TC_v2.0.xlsx | 3 | 3
TML_IPC_Wireless_Power_Charger_TC_v1.0.xlsx | 1 | 1
TML_Labcar_Clamp_Control_DVP_V3.9_21-06-24.xlsx | 1 | 1
TML_Labcar_ESCL_DVP_V4.0_20May24.xls | 1 | 1
TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 6 | 6
TML_Labcar_PassiveEntryExit_DVP_V3.6.xlsx | 1 | 1
TML_Labcar_PassiveStart_DVP_V3.9.xlsx | 1 | 1
TML_Labcar_PassiveTailgateControl_DVP_V3.3.xlsx | 1 | 1
TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 5 | 5
TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 22 | 22
TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 4 | 4
TML_X451_Q5_Labcar_Alarm_&_Security_DVP_2.5.xlsx | 1 | 1
TML_X451_Q5_Labcar_DriverWindow_Integration_In_BCM_DVP_V1.2_21-06-24.xls | 1 | 1
TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 17 | 17
TML_X451_Q5_X451_BCM_Labcar_Auto_Wipe_DVP_0.4.xlsx | 1 | 1
(blank)
Grand Total | 176 | 175

## Sheet3
Row Labels | Count of PASS | Count of No. of Test cases
Airbag |  | 22
TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx |  | 22
DID401A-01 |  | 1
DID401A-02 |  | 1
DID401A-04 |  | 1
DID401A-05 |  | 1
DID401B-01 |  | 1
DID401B-02 |  | 1
DID401B-03 |  | 1
DID401B-04 |  | 1
DID401B-05 |  | 1
DID401B-06 |  | 1
DID401B-07 |  | 1
DID401B-08 |  | 1
DID401B-09 |  | 1
DID401B-0A |  | 1
DID401B-0B |  | 1
DID401B-0C |  | 1
DID401B-0D |  | 1
DID401B-0E |  | 1
DID401B-0F |  | 1
DTC |  | 1
Func-PADS-PADI |  | 1
Func-SysWL |  | 1
BCM |  | 81
14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx |  | 5
Ambient Lighting |  | 1
Boot Lamp 1 |  | 1
Glove Box Lamp |  | 1
Puddle Lamp |  | 1
Roof Lamp |  | 1
15-TML_X451_Q5_Labcar_ORVM_DVP_V1.7.xlsx |  | 1
ORVM Fold_Unfold |  | 1
ORVM_Auto_Unfold_Feature_settings on HU_DVP_V0.4.xlsx |  | 1
ORVM Feature settiong on HU |  | 1
Switch illumination DVP_T_Logo_BCMC41_4_CW08.xlsx |  | 1
T_Logo |  | 1
TE_TML_X451_BCM_Labcar_AntiPinch_DVP_V1.3_9Feb'24.xls |  | 1
AutoPinchGeneral |  | 1
TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls |  | 38
Approach Light |  | 1
Auto_Head Lamp |  | 1
Batt Saver |  | 1
BCM UCS |  | 1
Cornering Function |  | 1
Crash Unlock |  | 1
DRL |  | 1
Express Cooling |  | 1
Flash_To_Pass |  | 1
Force Panic |  | 1
Fr Fog Lamp |  | 1
Front Washer |  | 1
Glove Box Lamp |  | 1
Hardware Wakeup |  | 1
Hazard |  | 1
Head_Lamp_leveling |  | 1
High_Beam |  | 1
Horn |  | 1
Lane Changer |  | 1
Lock Unlock |  | 1
Low_Beam |  | 1
Perimetric |  | 1
Position Lights_Reg platelamp_s |  | 1
Puddle |  | 1
Rear Washer |  | 1
Roof_Boot_KRI_Lamp |  | 1
RR Fog Lamp |  | 1
Stop Lamp |  | 1
Sunvisor Lamp |  | 1
Tail gate unlock |  | 1
Turn Indicator |  | 1
Vehicle Mislock |  | 1
Vehicle Seek |  | 1
Welcome Goodbye |  | 1
Window_Winding |  | 1
Wiper flick |  | 1
Wiper High Speed |  | 1
WiperLow Speed |  | 1
TML_Labcar_Clamp_Control_DVP_V3.9_21-06-24.xlsx |  | 1
Clamp Control for EV |  | 1
TML_Labcar_ESCL_DVP_V4.0_20May24.xls |  | 1
ESCL |  | 1
TML_Labcar_PassiveEntryExit_DVP_V3.6.xlsx |  | 1
Passive_EntryExit |  | 1
TML_Labcar_PassiveStart_DVP_V3.9.xlsx |  | 1
Passive_Start_EV |  | 1
TML_Labcar_PassiveTailgateControl_DVP_V3.3.xlsx |  | 1
Passive_Tailgate_Control |  | 1
TML_Labcar_Warning&Messages_DVP_V3.7.xlsx |  | 5
ACC ON Text Indication |  | 1
Audio Warning |  | 1
IGN ON Text Indication |  | 1
Press Brake Message |  | 1
WelCome Text Indication |  | 1
TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls |  | 4
FWAD |  | 1
FWLH |  | 1
RWC |  | 1
RWSC |  | 1
TML_X451_Q5_Labcar_Alarm_&_Security_DVP_2.5.xlsx |  | 1
Perimeter Alarm |  | 1
TML_X451_Q5_Labcar_DriverWindow_Integration_In_BCM_DVP_V1.2_21-06-24.xls |  | 1
DriverWindow_Integration_In_BCM |  | 1
TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx |  | 17
BrakeLamps & CHMSL |  | 1
AHL |  | 1
ApproachLights |  | 1
CorneringLamp |  | 1
CPL_SOC |  | 1
Daytime Running Lights |  | 1
FRONT ADAS |  | 1
FrontFogLamps |  | 1
Headlamp HighBeam |  | 1
Headlamp LowBeam |  | 1
LaneChanger |  | 1
Position Lamps |  | 1
REAR ADAS |  | 1
RearFogLamps |  | 1
Reverse Lights |  | 1
SBL |  | 1
Turn indicators & Hazards |  | 1
TML_X451_Q5_X451_BCM_Labcar_Auto_Wipe_DVP_0.4.xlsx |  | 1
Auto Wipe |  | 1
CCM |  | 4
Not Available |  | 1
FATC Acceptance Testing |  | 1
TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx |  | 2
Partner ECU |  | 1
User Input Control |  | 1
TML_Gen3_CCM_DVP_V1.0.xlsx |  | 1
FATC Functions |  | 1
CDC |  | 15
Not Available
CDC Acceptance Testing
TML_IPC_Door_Ajar_with_Bonnet_TC_v2.0.xlsx |  | 1
Door_Ajar_Mid_Variant |  | 1
TML_IPC_HighBeam_TC_v2.0.xlsx |  | 4
High Beam-CAN |  | 1
High Beam-Hardware |  | 1
Text Alert High Beam- Hardware |  | 1
Text Alert High Beam-CAN |  | 1
TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx |  | 2
PEPS Indication for ACC |  | 1
PEPS Indication for IGN |  | 1
TML_IPC_PositionLamp_DVP_v2.0 .xlsx |  | 2
Position_Lamp |  | 1
Text Alert |  | 1
TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx |  | 2
PowerModes |  | 1
WakeUP |  | 1
TML_IPC_TurnIndicator_TC_v2.0.xlsx |  | 3
Hazard |  | 1
Turn_Left_Indicator |  | 1
Turn_Right_Indicator |  | 1
TML_IPC_Wireless_Power_Charger_TC_v1.0.xlsx |  | 1
Wireless Power Charger(10.25") |  | 1
IVN |  | 1
Not Available |  | 1
IVN Acceptance Testing |  | 1
NA |  | 7
Not Applicable |  | 5
ECU software flashing and parameterisation |  | 1
Issue debugging and rectification |  | 1
Labcar Build |  | 1
Q current measurement ( Labcar & Individual ECU wise) |  | 1
Wiring Harness Updation |  | 1
ROWA_Electrical Check list |  | 1
Electrical check list |  | 1
ROWA_Labcar build Checkilst |  | 1
Labcar Build Check list |  | 1
SASS |  | 39
TC_V2_SkeyFobFD_V1_9thJan1.xlsx |  | 11
_Normal_Mode |  | 1
Approach_Light_Function |  | 1
Force_Panic_Scenarios_ |  | 1
General_Requirements |  | 1
Lock_Function |  | 1
Operating Voltage Range |  | 1
Operating_Modes |  | 1
Power_Consumption |  | 1
Tailgate_Open_Function |  | 1
Tailgate_Unlock_Function_ |  | 1
Unlock_Function |  | 1
TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx |  | 4
Follow-Me Home Feature |  | 1
SASS BCM Autolearning |  | 1
Vehicle Start Stop Feature |  | 1
Welcome Lighting Feature |  | 1
TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx |  | 5
KeyFob Approch Light |  | 1
Keyfob Force Panic |  | 1
KeyFob Tailgate Unlock |  | 1
KeyFob Vehicle Lock |  | 1
KeyFob Vehicle Unlock |  | 1
TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx |  | 19
BCM Auto Learning |  | 1
BCM Driver Passenger Lock |  | 1
BCM Driver Passenger Unlock |  | 1
BCM FollowMeHome Feature |  | 1
BCM Functional Zones |  | 1
BCM General Req |  | 1
BCM Personalization Feature |  | 1
BCM POT Closing |  | 1
BCM POT closingPEPSTailgateSwtc |  | 1
BCM POT Opening |  | 1
BCM POT openingPEPSTailgateSwtc |  | 1
BCM POT UID Fun Disabled |  | 1
BCM RKE Function |  | 1
BCM Tailgate Unlock |  | 1
BCM Vehicle Start Feature |  | 1
BCM WelcomeLight Feature |  | 1
PEPS Tailgate Trigger SASS-BCM |  | 1
POT ClosingThroughFasciaSwitch |  | 1
POT OpeningThroughFasciaSwitch |  | 1
SZM |  | 6
TML_Labcar_Memory_Seat_DVP_V0.2.xlsx |  | 6
DTC |  | 1
EEE |  | 1
Height_Movement |  | 1
MemoryRecallStore |  | 1
Slide_Movement |  | 1
Squab_Movement |  | 1
(blank)
(blank)
(blank)
Grand Total |  | 175

## ROWA_EV_Validation_Plan
P/A/U | Sl. No | Features | DVP Name | No. of Test cases | PASS | FAIL | NOT TESTED | NA | No. of days required | Controller ECU | Partner ECU | Controller ECU SW VER | Partner ECU SW VER | Controller ECU SW Release date | Partner ECU SW release date | SW avaliable date | Scope | Assigned to |  | 1 |  |  | 0 | 0
P | 1 | Labcar Build | Not Applicable | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2024-12-23 |  | 2024-12-31
A | [17 empty] | PRASANNA, SUSHMANTH | 2024-12-23 |  | 2024-12-31 | 100% | 0 | 0
P | 2 | Wiring Harness Updation | Not Applicable | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2024-12-31
A | [17 empty] | PRASANNA, SUSHMANTH |  |  |  | 90%
P | 3 | Labcar Build Check list | ROWA_Labcar build Checkilst | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2025-01-08 |  | 2025-01-09
A | [21 empty] | 100%
P | 4 | ECU software flashing and parameterisation | Not Applicable | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2025-01-06 |  | 2025-01-14
A | [21 empty] | 100%
P | 5 | Electrical check list | ROWA_Electrical Check list | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2025-01-20 |  | 2025-01-20
A | [21 empty] | 100%
P | 6 | Issue debugging and rectification | Not Applicable | NA |  |  |  |  | NA | NA | NA | [5 empty] | Labcar build | PRASANNA, SUSHMANTH | 2025-01-31 |  | 2025-03-13
A | [21 empty] | 100%
P | 7 | Q current measurement ( Labcar & Individual ECU wise) | Not Applicable | NA |  |  |  |  | NA | NA | NA | [5 empty] | Validation | PRASANNA, SUSHMANTH | NA |  | NA
A | [21 empty] | 100%
P | 8 | IVN Acceptance Testing | Not Available | NA |  |  |  |  | NA | IVN | NA | [5 empty] | Validation | PRASANNA, SUSHMANTH | NA |  | NA
A | [21 empty] | 100%
P | 9 | Position Lights_Reg platelamp_s | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 20 | 20 |  |  |  | 0.28571 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-03 |  | 2025-02-03
A
P | 10 | Lane Changer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 15 | 15 |  |  |  | 0.21429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-03 |  | 2025-02-03
A
P | 11 | Turn Indicator | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-03 |  | 2025-02-03
A
P | 12 | Hazard | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 20 | 20 |  |  |  | 0.28571 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-04 |  | 2025-02-04
A
P | 13 | DRL | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 20 | 20 |  |  |  | 0.28571 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-04 |  | 2025-02-04
A
P | 14 | Welcome Goodbye | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 0 | 0 |  |  |  | 0 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH
A | [21 empty] | 100%
P | 15 | Low_Beam | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 16 | 16 |  |  |  | 0.22857 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-05 |  | 2025-02-05
A
P | 16 | High_Beam | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 22 | 22 |  |  |  | 0.31429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-05 |  | 2025-02-05
A
P | 17 | Flash_To_Pass | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-06 |  | 2025-02-06
A
P | 18 | Head_Lamp_leveling | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 32 | 32 |  |  |  | 0.45714 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-06 |  | 2025-02-06
A
P | 19 | Auto_Head Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 | 8 |  |  |  | 0.11429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-06 |  | 2025-02-07
A
P | 20 | Roof_Boot_KRI_Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 26 | 26 |  |  |  | 0.37143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-07 |  | 2025-02-07
A | [18 empty] | 2025-02-12 |  | 2025-02-12 | 100%
P | 21 | Glove Box Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 16 | 16 |  |  |  | 0.22857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-07 |  | 2025-02-10
A | [18 empty] | 2025-02-12 |  | 2025-02-13 | 5%
P | 22 | Window_Winding | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 36 | 36 |  |  |  | 0.51429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-10 |  | 2025-02-10
A | [18 empty] | 2025-02-12 |  | 2025-02-12 | 100%
P | 23 | Approach Light | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 26 | 26 |  |  |  | 0.37143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-11 |  | 2025-02-11
A
P | 24 | Vehicle Seek | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 | 6 |  |  |  | 0.085714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-11 |  | 2025-02-11
A
P | 25 | Fr Fog Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 40 | 40 |  |  |  | 0.57143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-11 |  | 2025-02-12
A
P | 26 | RR Fog Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 | 4 |  |  |  | 0.057143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-12 |  | 2025-02-12
A
P | 27 | Cornering Function | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 | 4 |  |  |  | 0.057143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-12 |  | 2025-02-12
A
P | 28 | Stop Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 39 | 39 |  |  |  | 0.55714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-12 |  | 2025-02-13
A
P | 29 | Horn | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 18 | 18 |  |  |  | 0.25714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-13 |  | 2025-02-13
A
P | 30 | Perimetric | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 28 | 28 |  |  |  | 0.4 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-13 |  | 2025-02-14
A
P | 31 | Force Panic | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 |  | 4 |  |  | 0.057143 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-17 |  | 2025-02-17
A
P | 32 | Vehicle Mislock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 12 |  | 12 |  |  | 0.17143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-17 |  | 2025-02-17
A
P | 33 | Puddle | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  | 8 |  |  | 0.11429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-17 |  | 2025-02-17
A | [18 empty] | 2025-02-11 |  | 2025-02-11 | 100%
P | 34 | Sunvisor Lamp | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  | 8 |  |  | 0.11429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-18 |  | 2025-02-18
A
P | 35 | Hardware Wakeup | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 7 |  | 7 |  |  | 0.1 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-18 |  | 2025-02-18
A
P | 36 | BCM UCS | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 10 |  |  | 10 |  | 0.14286 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-18 |  | 2025-02-18
A
P | 37 | WiperLow Speed | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  |  | 8 |  | 0.11429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-18 |  | 2025-02-18
A | [18 empty] | 2025-02-11 |  | 2025-02-11 | 100%
P | 38 | Wiper High Speed | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 8 |  |  | 8 |  | 0.11429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-19 |  | 2025-02-19
A | [18 empty] | 2025-02-11 |  | 2025-02-11 | 100%
P | 39 | Wiper flick | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 12 |  |  | 12 |  | 0.17143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-20 |  | 2025-02-20
A | [18 empty] | 2025-02-11 |  | 2025-02-11 | 100%
P | 40 | Front Washer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 |  |  | 6 |  | 0.085714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-20 |  | 2025-02-20
A | [18 empty] | 2025-02-11 |  | 2025-02-11 | 100%
P | 41 | Rear Washer | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 6 |  |  | 6 |  | 0.085714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-20 |  | 2025-02-20
A | [18 empty] | 2025-02-12 |  | 2025-02-12 | 100%
P | 42 | Lock Unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 36 |  |  | 36 |  | 0.51429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-21 |  | 2025-02-21
A
P | 43 | Tail gate unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 24 |  |  | 24 |  | 0.34286 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-24 |  | 2025-02-25
A
P | 44 | Express Cooling | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 24 |  |  | 24 |  | 0.34286 | BCM | CCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-25 |  | 2025-02-26
A
P | 45 | Crash Unlock | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 4 |  |  | 4 |  | 0.057143 | BCM | AB12, CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-27 |  | 2025-02-27
A
P | 46 | Batt Saver | TML__BCM_Labcar_Acceptance_test_cases_labcar_CoC comment_V6.0.xls | 20 |  |  | 20 |  | 0.28571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-02-28 |  | 2025-02-28
A | [18 empty] | NA |  | NA | 100%
P | 47 | FATC Acceptance Testing | Not Available | 44 |  |  | 44 |  | 0.62857 | CCM | [6 empty] | Validation | PRASANNA, SUSHMANTH
A | [18 empty] | NA |  | NA | 100%
P | 48 | CDC Acceptance Testing | Not Available | [5 empty] | 0 | CDC | [6 empty] | Validation | PRASANNA, SUSHMANTH
A | [18 empty] | NA |  | NA | 100%
P | 49 | ORVM Feature settiong on HU | ORVM_Auto_Unfold_Feature_settings on HU_DVP_V0.4.xlsx | 29 |  |  | 29 |  | 0.41429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 03-03-2025 |  | 04-03-2025
A
P | 50 | ORVM Fold_Unfold | 15-TML_X451_Q5_Labcar_ORVM_DVP_V1.7.xlsx | 92 |  |  | 92 |  | 1.3143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 04-03-2025 |  | 06-03-2025
A
P | 51 | FWLH | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 16 |  |  | 16 |  | 0.22857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 06-03-2025 |  | 07-03-2025
A | [18 empty] | 2025-02-13 |  | 2025-02-13 | 100%
P | 52 | FWAD | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 9 |  |  | 9 |  | 0.12857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 07-03-2025 |  | 10-03-2025
A | [18 empty] | 2025-02-13 |  | 2025-02-13 | 100%
P | 53 | RWC | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 6 |  |  | 6 |  | 0.085714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 10-03-2025 |  | 10-03-2025
A | [18 empty] | 2025-02-14 |  | 2025-02-14 | 100%
P | 54 | RWSC | TML_X451_Q5_Labcar DVP_Wiper_Washer_V5.6.xls | 6 |  |  | 6 |  | 0.085714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 10-03-2025 |  | 10-03-2025
A
P | 55 | Roof Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 43 |  |  | 43 |  | 0.61429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 10-03-2025 |  | 11-03-2025
A | [21 empty] | 100%
P | 56 | Glove Box Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 36 |  |  | 36 |  | 0.51429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 11-03-2025 |  | 12-03-2025
A | [21 empty] | 100%
P | 57 | Puddle Lamp | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 36 |  |  | 36 |  | 0.51429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 12-03-2025 |  | 13-03-2025
A | [18 empty] | 2025-02-19 |  |  | 100%
P | 58 | Boot Lamp 1 | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 41 |  |  | 41 |  | 0.58571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 13-03-2025 |  | 14-03-2025
A | [21 empty] | 100%
P | 59 | Ambient Lighting | 14-TML_X451_Q5_Labcar_INL_DVP_V7.8_26May_2023.xlsx | 73 |  |  | 73 |  | 1.0429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 14-03-2025 |  | 17-03-2025
A
P | 60 | Turn indicators & Hazards | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 161 |  |  | 161 |  | 2.3 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 17-03-2025 |  | 20-03-2025
A
P | 61 | Position Lamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 64 |  |  | 64 |  | 0.91429 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 20-03-2025 |  | 21-03-2025
A
P | 62 | LaneChanger | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 44 |  |  | 44 |  | 0.62857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 21-03-2025 |  | 24-03-2025
A
P | 63 | Headlamp LowBeam | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 42 |  |  | 42 |  | 0.6 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 24-03-2025 |  | 25-03-2025
A
P | 64 | Headlamp HighBeam | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 54 |  |  | 54 |  | 0.77143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 25-03-2025 |  | 26-03-2025
A
P | 65 | BrakeLamps & CHMSL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 65 |  |  | 65 |  | 0.92857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 26-03-2025 |  | 27-03-2025
A
P | 66 | FrontFogLamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 62 |  |  | 62 |  | 0.88571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 27-03-2025 |  | 28-03-2025
A
P | 67 | RearFogLamps | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 56 |  |  | 56 |  | 0.8 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 28-03-2025 |  | 31-03-2025
A
P | 68 | ApproachLights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 39 |  |  |  | 39 | 0.55714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 31-03-2025 |  | 31-03-2025
A
P | 69 | Daytime Running Lights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 113 |  |  |  | 113 | 1.6143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 31-03-2025 |  | 02-04-2025
A
P | 70 | CorneringLamp | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 210 |  |  |  | 210 | 3 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 02-04-2025 |  | 07-04-2025
A
P | 71 | Reverse Lights | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 76 |  |  |  | 76 | 1.0857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 07-04-2025 |  | 08-04-2025
A
P | 72 | AHL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 10 |  |  |  | 10 | 0.14286 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 08-04-2025 |  | 09-04-2025
A
P | 73 | SBL | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 11 |  |  |  | 11 | 0.15714 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 09-04-2025 |  | 10-04-2025
A
P | 74 | FRONT ADAS | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 19 |  |  |  | 19 | 0.27143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 10-04-2025 |  | 11-04-2025
A
P | 75 | REAR ADAS | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 30 |  |  |  | 30 | 0.42857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 11-04-2025 |  | 14-04-2025
A
P | 76 | CPL_SOC | TML_X451_Q5_X1_X0_BCM_Labcar_Exterior_Lights_DVP_v2.8_1 APRIL'24.xlsx | 84 |  |  |  | 84 | 1.2 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 14-04-2025 |  | 16-04-2025
A
P | 77 | Auto Wipe | TML_X451_Q5_X451_BCM_Labcar_Auto_Wipe_DVP_0.4.xlsx | 92 |  |  |  | 92 | 1.3143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 16-04-2025 |  | 18-04-2025
A | [18 empty] | 2025-02-17 |  | 2025-02-18 | 100%
P | 78 | Press Brake Message | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 33 |  |  |  | 33 | 0.47143 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 18-04-2025 |  | 21-04-2025
A
P | 79 | ACC ON Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 42 |  |  |  | 42 | 0.6 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 21-04-2025 |  | 22-04-2025
A
P | 80 | IGN ON Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 42 |  |  |  | 42 | 0.6 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 22-04-2025 |  | 23-04-2025
A
P | 81 | WelCome Text Indication | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 22 |  |  |  | 22 | 0.31429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 23-04-2025 |  | 24-04-2025
A
P | 82 | Audio Warning | TML_Labcar_Warning&Messages_DVP_V3.7.xlsx | 44 |  |  |  | 44 | 0.62857 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 24-04-2025 |  | 25-04-2025
A
P | 83 | DriverWindow_Integration_In_BCM | TML_X451_Q5_Labcar_DriverWindow_Integration_In_BCM_DVP_V1.2_21-06-24.xls | 92 |  |  |  | 92 | 1.3143 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 25-04-2025 |  | 29-04-2025
A | [18 empty] | 2025-03-13 |  | 2025-03-14 | 100%
P | 84 | AutoPinchGeneral | TE_TML_X451_BCM_Labcar_AntiPinch_DVP_V1.3_9Feb'24.xls | 69 |  |  |  | 69 | 0.98571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 29-04-2025 |  | 30-04-2025
A
P | 85 | Clamp Control for EV | TML_Labcar_Clamp_Control_DVP_V3.9_21-06-24.xlsx | 186 |  |  |  | 186 | 2.6571 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 30-04-2025 |  | 05-05-2025
A
P | 86 | Passive_EntryExit | TML_Labcar_PassiveEntryExit_DVP_V3.6.xlsx | 581 |  |  |  | 581 | 8.3 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 05-05-2025 |  | 15-05-2025
A
P | 87 | Passive_Tailgate_Control | TML_Labcar_PassiveTailgateControl_DVP_V3.3.xlsx | 57 |  |  |  | 57 | 0.81429 | BCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 15-05-2025 |  | 16-05-2025
A
P | 88 | Passive_Start_EV | TML_Labcar_PassiveStart_DVP_V3.9.xlsx | 174 |  |  |  | 174 | 2.4857 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 16-05-2025 |  | 21-05-2025
A
P | 89 | BCM Functional Zones | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 23 | 23 |  |  |  | 0.32857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 21-05-2025 |  | 22-05-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 90 | BCM General Req | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 178 | 178 |  |  |  | 2.5429 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 22-05-2025 |  | 27-05-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 91 | BCM Driver Passenger Unlock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 175 | 175 |  |  |  | 2.5 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 27-05-2025 |  | 30-05-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 92 | BCM Driver Passenger Lock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 629 | 629 |  |  |  | 8.9857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 30-05-2025 |  | 12-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 93 | BCM Tailgate Unlock | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 176 | 176 |  |  |  | 2.5143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 12-06-2025 |  | 17-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 94 | BCM Auto Learning | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 4 | 4 |  |  |  | 0.057143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 17-06-2025 |  | 17-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 95 | BCM Vehicle Start Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 75 | 75 |  |  |  | 1.0714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 17-06-2025 |  | 18-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 96 | BCM RKE Function | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 285 | 285 |  |  |  | 4.0714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 18-06-2025 |  | 24-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 97 | BCM WelcomeLight Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 17 | 17 |  |  |  | 0.24286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 24-06-2025 |  | 25-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 98 | BCM FollowMeHome Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 17 | 17 |  |  |  | 0.24286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 25-06-2025 |  | 26-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 99 | BCM Personalization Feature | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 91 | 91 |  |  |  | 1.3 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 26-06-2025 |  | 27-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 100 | BCM POT Opening | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 63 | 63 |  |  |  | 0.9 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 27-06-2025 |  | 30-06-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 101 | BCM POT Closing | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 63 | 63 |  |  |  | 0.9 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 30-06-2025 |  | 01-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 102 | BCM POT UID Fun Disabled | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 4 | 4 |  |  |  | 0.057143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 01-07-2025 |  | 01-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 103 | BCM POT openingPEPSTailgateSwtc | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 33 | 33 |  |  |  | 0.47143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 01-07-2025 |  | 02-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 104 | BCM POT closingPEPSTailgateSwtc | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 33 | 33 |  |  |  | 0.47143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 02-07-2025 |  | 03-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 105 | PEPS Tailgate Trigger SASS-BCM | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 57 | 57 |  |  |  | 0.81429 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 03-07-2025 |  | 04-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 106 | POT OpeningThroughFasciaSwitch | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 35 | 35 |  |  |  | 0.5 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 04-07-2025 |  | 07-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 107 | POT ClosingThroughFasciaSwitch | TestCases_TML SASS_BCM Interface Requirement_V2.2.xlsx | 30 | 30 |  |  |  | 0.42857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 07-07-2025 |  | 08-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 108 | Operating Voltage Range | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 6 | 6 |  |  |  | 0.085714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 08-07-2025 |  | 08-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 109 | Power_Consumption | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 9 | 9 |  |  |  | 0.12857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 08-07-2025 |  | 09-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 110 | General_Requirements | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 13 | 13 |  |  |  | 0.18571 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 09-07-2025 |  | 10-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 111 | _Normal_Mode | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 7 | 7 |  |  |  | 0.1 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 10-07-2025 |  | 11-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 112 | Lock_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 | 24 |  |  |  | 0.34286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 11-07-2025 |  | 14-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 113 | Unlock_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 | 24 |  |  |  | 0.34286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 14-07-2025 |  | 15-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 114 | Approach_Light_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 23 | 23 |  |  |  | 0.32857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 15-07-2025 |  | 16-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 115 | Tailgate_Unlock_Function_ | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 | 24 |  |  |  | 0.34286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 16-07-2025 |  | 17-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 116 | Tailgate_Open_Function | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 24 | 24 |  |  |  | 0.34286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 17-07-2025 |  | 18-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 117 | Force_Panic_Scenarios_ | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 25 | 25 |  |  |  | 0.35714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 18-07-2025 |  | 21-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 118 | Operating_Modes | TC_V2_SkeyFobFD_V1_9thJan1.xlsx | 6 | 6 |  |  |  | 0.085714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 21-07-2025 |  | 21-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 119 | Vehicle Start Stop Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 172 | 172 |  |  |  | 2.4571 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 21-07-2025 |  | 24-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 120 | Welcome Lighting Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 91 | 91 |  |  |  | 1.3 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 24-07-2025 |  | 25-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 121 | Follow-Me Home Feature | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 70 | 70 |  |  |  | 1 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 25-07-2025 |  | 28-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 122 | SASS BCM Autolearning | TestCases_Smart_DK_Zone_Detection_TML_SASS_Function_DVP_V1.1.xlsx | 9 | 9 |  |  |  | 0.12857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 28-07-2025 |  | 29-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 123 | KeyFob Vehicle Lock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 116 | 116 |  |  |  | 1.6571 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 29-07-2025 |  | 31-07-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 124 | KeyFob Vehicle Unlock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 68 | 68 |  |  |  | 0.97143 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 31-07-2025 |  | 01-08-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 125 | KeyFob Approch Light | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 18 | 18 |  |  |  | 0.25714 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 01-08-2025 |  | 04-08-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 126 | KeyFob Tailgate Unlock | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 86 | 86 |  |  |  | 1.2286 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 04-08-2025 |  | 06-08-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 127 | Keyfob Force Panic | TestCases_Smart_KeyFob_TML_SASS_Function_DVP_V1.1.xlsx | 9 | 9 |  |  |  | 0.12857 | SASS | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 06-08-2025 |  | 07-08-2025 |  |  |  | SASS TC partially testable on LABCAR
A
P | 128 | ESCL | TML_Labcar_ESCL_DVP_V4.0_20May24.xls | 186 | 186 |  |  |  |  | BCM | ESCL | [5 empty] | Validation | PRASANNA, SUSHMANTH | 07-08-2025 |  | 12-08-2025
A
P | 129 | User Input Control | TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx | 1283 | 1283 |  |  |  | 17.1067 | CCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 12-08-2025 |  | 14-08-2025
A | [18 empty] | 2025-04-22 |  | 2025-05-02 | 100%
P | 130 | FATC Functions | TML_Gen3_CCM_DVP_V1.0.xlsx | 0 | 0 |  |  |  | 0 | CCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 14-08-2025 |  | 19-08-2025
A
P | 131 | Partner ECU | TE_TML_Rowa_Full_Validation_DVP_v1.0.xlsx | 319 | 319 |  |  |  | 4.2533 | CCM | CDC | [5 empty] | Validation | PRASANNA, SUSHMANTH | 19-08-2025 |  | 22-08-2025
A | [18 empty] | 2025-04-17 |  | 2025-04-22 | 100%
P | 132 | Door_Ajar_Mid_Variant | TML_IPC_Door_Ajar_with_Bonnet_TC_v2.0.xlsx | 263 | 263 |  |  |  | 3.7571 | CDC | [6 empty] | Validation | PRASANNA, SUSHMANTH | 22-08-2025 |  | 28-08-2025
A | [18 empty] | 2025-05-21 |  | 2025-05-26 | 20%
P | 133 | High Beam-CAN | TML_IPC_HighBeam_TC_v2.0.xlsx | 31 | 31 |  |  |  | 0.44286 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 28-08-2025 |  | 29-08-2025
A
P | 134 | High Beam-Hardware | TML_IPC_HighBeam_TC_v2.0.xlsx | 0 |  |  | 0 |  | 0 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 29-08-2025 |  | 01-09-2025 |  |  |  | NA
A
P | 135 | Text Alert High Beam-CAN | TML_IPC_HighBeam_TC_v2.0.xlsx | 7 |  |  | 7 |  | 0.1 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 01-09-2025 |  | 02-09-2025
A
P | 136 | Text Alert High Beam- Hardware | TML_IPC_HighBeam_TC_v2.0.xlsx | 0 |  |  | 0 |  | 0 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 02-09-2025 |  | 03-09-2025 |  |  |  | NA
A
P | 137 | Position_Lamp | TML_IPC_PositionLamp_DVP_v2.0 .xlsx | 39 |  |  | 39 |  | 0.55714 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 03-09-2025 |  | 03-09-2025
[19 empty] | 2025-05-20 |  | 2025-05-20 | 100%
P | 138 | Text Alert | TML_IPC_PositionLamp_DVP_v2.0 .xlsx | 40 |  |  | 40 |  | 0.57143 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 03-09-2025 |  | 04-09-2025
[19 empty] | 2025-05-20 |  | 2025-05-20 | 100%
P | 139 | PowerModes | TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx | 0 |  |  | 0 |  | 0.38571 | CDC | [6 empty] | Validation | PRASANNA, SUSHMANTH | 04-09-2025 |  | 05-09-2025 |  |  |  | NA
P | 140 | WakeUP | TML_IPC_Q5_MCE_PowerModes _WakeUp_Strategy_TC_v3.0.xlsx | 0 |  |  | 0 |  | 0.14286 | CDC | [6 empty] | Validation | PRASANNA, SUSHMANTH | 05-09-2025 |  | 08-09-2025 |  |  |  | NA
P | 141 | Turn_Left_Indicator | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 26 |  |  | 26 |  | 0.37143 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 08-09-2025 |  | 09-09-2025
P | 142 | Turn_Right_Indicator | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 26 |  |  | 26 |  | 0.37143 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 09-09-2025 |  | 10-09-2025
P | 143 | Hazard | TML_IPC_TurnIndicator_TC_v2.0.xlsx | 25 |  |  | 25 |  | 0.35714 | CDC | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 10-09-2025 |  | 11-09-2025
P | 144 | Wireless Power Charger(10.25") | TML_IPC_Wireless_Power_Charger_TC_v1.0.xlsx | 52 |  |  | 52 |  | 0.74286 | CDC | [6 empty] | Validation | PRASANNA, SUSHMANTH | 11-09-2025 |  | 12-09-2025
[22 empty] | 100% |  |  | Completed in Sierra
P | 145 | DID401A-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 60 |  |  | 60 |  | 0.94286 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 12-09-2025 |  | 16-09-2025
[19 empty] | 2025-03-25 |  | 2025-03-25 | 100%
P | 147 | DID401A-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 60 |  |  | 60 |  | 0.84286 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-17 |  | 2025-09-17
[19 empty] | 2025-03-26 |  | 2025-03-28 | 100%
P | 148 | DID401A-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 77 |  |  | 77 |  | 1.1 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-17 |  | 2025-09-18
[19 empty] | 2025-03-03 |  | 2025-03-04 | 100%
P | 149 | DID401A-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 33 |  |  | 33 |  | 0.47143 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-19 |  | 2025-09-19
[19 empty] | 2025-04-03 |  | 2025-04-03 | 100%
P | 150 | DID401B-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 |  |  | 171 |  | 2.4429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-19 |  | 2025-09-23
[19 empty] | 2025-04-03 |  | 2025-04-07 | 100%
P | 151 | DID401B-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 |  |  | 171 |  | 2.4429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-24 |  | 2025-09-26
[19 empty] | 2025-04-08 |  | 2025-04-11 | 100%
P | 152 | DID401B-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 126 |  |  | 126 |  | 1.8 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-26 |  | 2025-09-30
[19 empty] | 2025-04-11 |  | 2025-04-14 | 100%
P | 153 | DID401B-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 279 |  |  | 279 |  | 3.9857 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-09-30 |  | 2025-10-03
[19 empty] | 2025-03-04 |  | 2025-03-07 | 100%
P | 154 | DID401B-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 2.7857 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-05 |  | 2025-10-07 |  |  |  | NA
P | 155 | DID401B-06 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 3.3 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-08 |  | 2025-10-13 |  |  |  | NA
P | 156 | DID401B-07 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 2.7857 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-14 |  | 2025-10-16 |  |  |  | NA
P | 157 | DID401B-08 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 3.3 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-17 |  | 2025-10-22 |  |  |  | NA
P | 158 | DID401B-09 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 2.7857 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-23 |  | 2025-10-27 |  |  |  | NA
P | 159 | DID401B-0A | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 81 |  |  | 81 |  | 1.1571 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-28 |  | 2025-10-28
[19 empty] | 2025-06-03 |  | 2025-06-04 | 100%
P | 160 | DID401B-0B | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 156 |  |  | 156 |  | 2.2286 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-29 |  | 2025-10-31
[19 empty] | 2025-03-10 |  | 2025-03-12 | 100%
P | 161 | DID401B-0C | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 |  |  | 129 |  | 1.8429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-10-31 |  | 2025-11-03 |  |  |  | NA
[19 empty] | 2025-06-04 |  | 2025-06-05 | 100%
P | 162 | DID401B-0D | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 |  |  | 129 |  | 1.8429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-04 |  | 2025-11-05 |  |  |  | NA
[19 empty] | 2025-06-05 |  | 2025-06-06 | 100%
P | 163 | DID401B-0E | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 108 |  |  | 108 |  | 1.5429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-05 |  | 2025-11-06 |  |  |  | NA
[19 empty] | 2025-06-06 |  | 2025-06-09 | 100%
P | 164 | DID401B-0F | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 0 |  |  | 0 |  | 1.8429 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-07 |  | 2025-11-10 |  |  |  | NA
P | 165 | Func-SysWL | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 6 |  |  | 6 |  | 0.085714 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-10 |  | 2025-11-10 |  |  |  | NA
P | 166 | Func-PADS-PADI | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 28 |  |  | 28 |  | 0.4 | Airbag | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-10 |  | 2025-11-10
[19 empty] | 2025-03-12 |  | 2025-03-12 | 100%
P | 167 | DTC | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 130 |  |  | 130 |  | 1.8571 | Airbag | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-11 |  | 2025-11-12
P |  | Squab_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  | 95 |  | 1.58 | SZM | BCM | [7 empty] | 2025-11-12 |  | 2025-11-13
[19 empty] | 2025-05-12 |  | 2025-05-13 | 100%
P |  | Slide_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  | 95 |  | 1.5833 | SZM | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-13 |  | 2025-11-14
[19 empty] | 2025-05-13 |  | 2025-05-14 | 100%
P |  | Height_Movement | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 95 |  |  | 95 |  | 1.5833 | SZM | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-17 |  | 2025-11-18
[19 empty] | 2025-05-15 |  | 2025-05-19 | 100%
P |  | MemoryRecallStore | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 91 |  |  | 91 |  | 1.5167 | SZM | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-18 |  | 2025-11-19 |  |  |  | DVP needs to be updated
P |  | DTC | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 43 |  |  | 43 |  | 0.71667 | SZM | BCM | [5 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-19 |  | 2025-11-20 |  |  |  | DVP needs to be updated
P |  | EEE | TML_Labcar_Memory_Seat_DVP_V0.2.xlsx | 12 |  |  | 12 |  | 0.2 | SZM | BCM | [13 empty] | DVP needs to be updated
|  | T_Logo | Switch illumination DVP_T_Logo_BCMC41_4_CW08.xlsx | 88 |  |  | 88 |  | 1.2571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-21 |  | 2025-11-24
|  | Perimeter Alarm | TML_X451_Q5_Labcar_Alarm_&_Security_DVP_2.5.xlsx | 87 |  |  | 87 |  | 1.2571 | BCM | [6 empty] | Validation | PRASANNA, SUSHMANTH | 2025-11-25 |  | 2025-11-26
|  | PEPS Indication for IGN | TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx | 23 |  |  | 23 |  | 0.32857 | CDC | BCM | [5 empty] | Validation |  | 2025-05-27 |  | 2025-05-27
|  | PEPS Indication for ACC | TML_IPC_PEPS Indication( IGN & ACC)_TC_v1.0.xlsx | 19 |  |  | 19 |  | 0.27143 | CDC | BCM | [5 empty] | Validation |  | 2025-05-27 |  | 2025-05-27

## User Notes
| Sr. No. | Notes
| 1 | Do not insert any row or column in the planning sheet.
| 2 | The cells marked with red blocks are to be updated by user.
| 3 | The new tasks are to be added in a sequential manner.
| 4 | For any task there will be two rows : Planned and Actual.
| 5 | The task deferred is to be mentioned in column "Task Deferred"
| 6 | Sundays and Holidays are not considered.
| 7 | There will different worksheets for different vehicle variants.
| 8 | Changes in SW drop will be termed as "Deferred" and new Task will be added with the updated timeline.
| 9 | Unplanned Task will be appended to the list and also have Actual time spent.
147 | DID401A-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 59 | 0.84286 | Airbag
148 | DID401A-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 77 | 1.1 | Airbag | Validation
149 | DID401A-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 33 | 0.47143 | Airbag | Validation
150 | DID401B-01 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 | 2.4429 | Airbag | Validation
151 | DID401B-02 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 171 | 2.4429 | Airbag | Validation
152 | DID401B-03 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 126 | 1.8 | Airbag | Validation
153 | DID401B-04 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 279 | 3.9857 | Airbag | Validation
154 | DID401B-05 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
155 | DID401B-06 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 231 | 3.3 | Airbag | Validation
156 | DID401B-07 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
157 | DID401B-08 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 231 | 3.3 | Airbag | Validation
158 | DID401B-09 | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 195 | 2.7857 | Airbag | Validation
159 | DID401B-0A | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 81 | 1.1571 | Airbag | Validation
160 | DID401B-0B | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 156 | 2.2286 | Airbag | Validation
161 | DID401B-0C | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
162 | DID401B-0D | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
163 | DID401B-0E | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 108 | 1.5429 | Airbag | Validation
164 | DID401B-0F | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 129 | 1.8429 | Airbag | Validation
165 | Func-SysWL | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 6 | 0.085714 | Airbag | Validation
166 | Func-PADS-PADI | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 28 | 0.4 | Airbag | Validation
167 | DTC | TML_SRS_Conti_Test_Cases_Ver0_1_20250214.xlsx | 130 | 1.8571 | Airbag | Validation
Validation
Validation
Validation
Validation
Validation
Validation
Validation
Validation

## DVP_List
Sr. No. | DVP Name and Version | Total No.of test cases | No. of Days require to execute the DVP | Testing Type | Applicable ECU | DVP Prepared By | SVN Link
1